## Sprint 1 Burndown
EHDA PORTAL ¦ SPRINT 1 BURNDOWN
Foundation Sprint • Planned Oct 10–14, 2026 • Actual completion Oct 16 • Scrum Master: Madina Afshar
Planned points | 33 | Actual daily records | 7 of 7 entered
Day / Date | Ideal remaining | Completed today ★ | Cumulative done | Actual remaining | Actual progress / evidence notes
Sprint start | 33 | 0 | 0 | 33
Oct 10 (Day 1) | 26.4 | 8 | 8 | 25 | Prject Foundation Database, Registration and Validation
Oct 11 (Day 2) | 19.8 | 8 | 16 | 17 | Session and Login, password security and access control
Oct 12 (Day 3) | 13.2 | 5 | 21 | 12 | Donor Profile Fields
Oct 13 (Day 4) | 6.6 | 2 | 23 | 10 | Store Donor Information
Oct 14 (Day 5) | 0 | 2 | 25 | 8 | Avaiable and unavailable
Oct 15 (Day 6) | 0 | 3 | 28 | 5 | Input Validation and Error Handling
Oct 16 (Day 7) | 0 | 5 | 33 | 0 | Initial Testing and Defect Tracking
SPRINT RESULT • All 33 points completed on Oct 16, two calendar days after the planned Oct 14 finish.

## Sprint 1 Scope
EHDA PORTAL ¦ SPRINT 1 SCOPE
Planned items and estimates copied from the uploaded Product Backlog and Sprint Backlog.
Backlog ID | Sprint 1 Task | Story Points | Responsible | Status (uploaded backlog) | Notes
#021 | Project structure & database connection | 5 | Samira Azizi | Completed | Project foundation / database
#001 | User registration | 3 | Samira Azizi | Completed | Registration and validation
#002 | Login and logout | 3 | Samira Azizi | Completed | Sessions and login
#022 | Authentication security & permissions | 5 | Samira Azizi | Completed | Password security and access control
#003 | Create / update donor profile | 5 | Samira Azizi | Completed | Donor profile fields
#004 | Blood type & availability fields | 2 | Samira Azizi | Completed | Store donor information
#005 | Change donor availability status | 2 | Samira Azizi | Completed | Available / unavailable
#024 | Input validation and error handling | 3 | All developers | Completed | Sprint 1 portion only
#025 | Initial testing and defect tracking | 5 | All developers | Completed | Sprint 1 portion only
TOTAL SPRINT 1 PLAN |  | 33