## Sprint 2 Burndown
EHDA PORTAL ¦ SPRINT 2 BURNDOWN
Donor Search & Map • Oct 17–22, 2026 • Illustrative daily progress • Scrum Master: Madina Afshar
Planned points | 37 | Daily records | 6 of 6 illustrated
Day / Date | Ideal remaining | Illustrative done ★ | Cumulative done | Illustrative remaining | Scenario notes — replace after verifying
Sprint start | 37 | 0 | 0 | 37 | Scenario only, not verified progress
Oct 17 (Day 1) | 30.8 | 0 | 0 | 37 | Kickoff / setup; no story marked Done
Oct 18 (Day 2) | 24.7 | 5 | 5 | 32 | Illustration: #006 blood-type search accepted
Oct 19 (Day 3) | 18.5 | 3 | 8 | 29 | Illustration: #009 approximate donor locations accepted
Oct 20 (Day 4) | 12.3 | 5 | 13 | 24 | Illustration: #007 location/distance search accepted
Oct 21 (Day 5) | 6.2 | 5 | 18 | 19 | Illustration: #010 blood requests accepted; 18/37 points done
Oct 22 (Day 6) | 0 | 19 | 37 | 0 | UNVERIFIED example: #023, #008, #024, #025 accepted
37
ILLUSTRATIVE ONLY • Assumes 18/37 points by Oct 21 and completion on Oct 22. Verify against actual Done stories and test evidence.

## Sprint 2 Scope
EHDA PORTAL ¦ SPRINT 2 SCOPE
Sprint 2 plan from your updated backlog (Oct 17–22). Estimates from Product Backlog; statuses/daily completion are unverified.
Backlog ID | Sprint 2 Task | Story Points | Responsible | Scenario status | Notes
#006 | Search donors by blood type | 5 | Ahmad Kaihan Saba | Illustrative Done | Donor blood type matching
#007 | Search by location or distance | 5 | Ahmad Kaihan Saba | Illustrative Done | Location and radius filters
#009 | Display approximate locations | 3 | Ahmad Kaihan Saba | Illustrative Done | Do not show exact home addresses
#023 | Protect donor privacy | 3 | Samira Azizi / Ahmad Kaihan Saba | Illustrative Done | Shared across Sprint 1 and 2; verify allocation
#008 | Interactive map | 8 | Ahmad Kaihan Saba | Illustrative Done | Moved from Sprint 3 in Product Backlog
#010 | Create and send blood requests | 5 | Shafiqa Taraki | Illustrative Done | Moved from Sprint 3 in Product Backlog
#024 | Input validation and error handling | 3 | All developers | Illustrative Done | Shared across Sprints 1–4; verify allocation
#025 | Search, privacy, request testing | 5 | All developers | Illustrative Done | Shared across Sprints 1–4; verify allocation
TOTAL SPRINT 2 PLAN |  | 37