## Product Backlog Template
Ehda Portal Backlog Document
Backlog Item ID | Type of Backlog Item | Description | Priority | Story Points | Status | Sprint | Assignee | Acceptance Criteria
#001 | User Story | As a new user, I want to create an account so that I can access the platform’s features. | Critical | 3 | To Do | Sprint 1 | Samira Azizi | User can enter registration information; systemvalidates the required fields; duplicate accounts are not accepted; account is registered successfully
#002 | User Story | As a user, I want to log in and log out do that I can access and protect my account. | Critical | 3 | To Do | Sprint 1 | Samira Azizi | Registered users can log in with their credentials; Invalid credentials should not be logged in; users can log out; After log out, the users should not be able to access the content
#003 | User Story | As a donor, I want to create and update my donor profile so that people who need blood can find information about me. | Critical | 5 | To Do | Sprint 1 | Samira Azizi | Donor can create a profile; user can add profile information; donor can update their information; updated information is saved; donor can control what information is shown to other users
#004 | User Story | As a donor, I want to specify my blood type and availability so that the blood seekers can identify suitable donors. | Critical | 2 | To Do | Sprint 1 | Samira Azizi | Donor can select blood type; donor can show availability status; blood type is displayed in the profile; the information can be updated
#005 | User Story | As a donor, I want to control my availability status whether I am currently available or not. | High | 2 | To Do | Sprint 1 | Samira Azizi | Donors can set their availability status; donor can change their availability status; search results shows availability status; unvailable donors are identified
#006 | User Story | As a blood seeker, I want to search for donors based on their blood type so that I can find donors who match the blood type I need. | Critical | 5 | To Do | Sprint 2 | Ahmad Kaihan Saba | Blood seekers can select their required blood type; system displays matching blood type donors; result shows information about the donors
#007 | User Story | As a blood seeker, I want to search for donors based on their location and distance so that I can find donors who are nearby. | Critical | 5 | To Do | Sprint 2 | Ahmad Kaihan Saba | Blood seekers can provide a location; blood seekers can specify the distance they want to search within; system displays nearby donors; result is ordered based on the result
#008 | User Story | As a user, I want to view a map of nearby donors, hospitals, and donation centers so that I can identify their locations easily. | High | 8 | To Do | Sprint 3 | Ahmad Kaihan Saba | Users can open a map; nearby medical facilities are shown; donors are represented based on their locations; users can interact with the map and find locations
#009 | User Story | As a donor, I want to share my approximate location not the exact home address to protect my privacy. | High | 3 | To Do | Sprint 2 | Ahmad Kaihan Saba | Exct home addresses are not shown to the users; approxximate locations are used; donor location information is handled securely
#010 | User Story | As a blood seeker, I want to send blood request to a donor so that I can ask for help when I need the blood. | Critical | 5 | To Do | Sprint 3 | Shafiqa Taraki | Blood seekers can select donors; blood seekers can provide request information; system records the request; donors receive the requests; requestes have status like pending, accepted, or declined
#011 | User Story | As a donor, I want to receive notifications about blood requests so that I know when someone needs my help. | High | 3 | To Do | Sprint 3 | Shafiqa Taraki | Donor receives a notification when request is received; notificaation identifies that the request is received; donor can open the request; request status can change
#012 | User Story | As a donor, I want to accept or decline a blood request so that I can choose whether I am able to respond or not. | High | 3 | To Do | Sprint 3 | Shafiqa Taraki | Donors can view pending requests; donors can accept requests; donors can decline requests; system updates request status; blood seekers are informed of the response
#013 | User Story | As a blood seeker, I want to receive the donor’s response to my request so that I know whether the donor can help me or not. | High | 2 | To Do | Sprint 3 | Shafiqa Taraki | Blood seekers can view requests; request status is clearly displayed; blood seeker is notified of the response; accepted and declied requests are distinguished
#014 | User Story | As a donor and blood seeker, I want to message after a request is accepted so that we can talk about the donation. | High | 5 | To Do | Sprint 3 | Shafiqa Taraki | Messaging option becomes available when the request is accepted; both donor and seeker can message; messages are displayed in a chat; users can see previous messages; users cannot message before a request is accepted
#015 | User Story | As a donor, I want to record my blood donations so that I can keep track of my donation history. | Medium | 3 | To Do | Sprint 4 | Samira Azizi | Donor can add to their donation record; donor can enter donation information; previous donations are shown in chronological order; donor can update a record; donation history is private
#016 | User Story | As a user, I want to manage my account information so that my personal information remains up to date. | Medium | 3 | To Do | Sprint 4 | Samira Azizi | User can see their account information; user can update their information; system can validate the pdated information; cahnges are saved; sensetive information is protected
#017 | User Story | As an administrator, I want to view and manage registers users so that I can maintain the platform properly. | Medium | 5 | To Do | Sprint 4 | Shafiqa Taraki | Admin can view the registered users; admin can search users; admin can view account information; admin can manage the accounts; only authorized members can do these actions
#018 | User Story | As an administrator, I want to manage hospitals and blood donation centers so that users can access accurate information about their locations. | Medium | 5 | To Do | Sprint 4 | Shafiqa Taraki | Admin can add hospitals and donation centers; admins can update the information; location information is displayed correctly; only authorized admins can manage locations
#019 | User Story | As an administrator, I want to review reported accounts and take appropriate action so that the platform remains safe. | Medium | 5 | To Do | Sprint 4 | Shafiqa Taraki | Users can rerport accounts; admins can view reported accounts; admins can review the report information; admin can take actions
#020 | User Story | As an administrator, I want to monitor and manage blood requests and platform activities so that I can help maintain proper operation of the system. | Medium | 8 | To Do | Sprint 4 | Shafiqa Taraki | Admin can view blood requests activities; admins can monitor the request status
#021 | Technical Task | Esablish the project structure, connect the application to a database, and create the initial database schema for users, donor profiles, and related platforms | Critical | 5 | To Do | Sprint 1 | Samira Azizi | Project structure is created; the database connection works; tables and relationships are defined; the team can run the application
#022 | Quality Requirement | Implement security controls for authentication, passwords, sessions, and role-based access | Critical | 5 | To DO | Sprint 1 | Samira Azizi | Passwords are stored using secure password hashing; authenticated users can access the features; authorized administrators can access administrative functions; Users cannot access another user's private information
#023 | Quality Requirement | Protect donor privacy | Critical | 3 | To DO | 1-2 | Samira Azizi + Ahmad Kaihan Saba | Exact home addresses and account information are not shown in public results
#024 | Technical Task | Validate user input and handle errors consistently | High | 3 | To DO | 1-4 | All developers | Requird dields and invalid inputs are checked; users receive errors
#025 | Technical Task | Prepare and execute test cases, fix if needed, retest the fixes | Critical | 5 | To DO | 1-4 | All developers | There should be documented test cases and their results; everything is recorded; defects are fixed and retested
#026
#027
#028