## Blank sheet
Sprint Backlog - Ehda Portal | [6 empty] | Approved
Sprint Name | Ehda Portal - Sprint Planning | Start Date | 2026-10-10 | Overall Progress |  |  | Needs Review
Manager | Madina Pasun, Madina Afshar | End Date | 2026-10-26 | Deliverables | Blood donation platform, source code, documentation, diagrams, testing evidence, dinal demo |  | On Hold
Task Name | Responsible | Start | Finish | Duration in days | Status | Notes
SPRINT 1 - Foundation | All team | 2026-10-10 | 2026-10-14 | 5 | In Progress | Build the account and database foundation | Not Started
#021 - Project Structure and Database Connection | Samira Azizi | 2026-10-11 | 2026-10-12 | 2 | In Progress | Set up the project structure, database connection, and tables | Not Started
#001 - User Registration | Samira Azizi | 2026-10-11 | 2026-10-13 | 3 | In Progress | Create an account and validate required information | Not Started
#002 Login and Logout | Samira Azizi | 2026-10-11 | 2026-10-13 | 3 | Not Started | implement login, logout, and session handling
#022 - Authentication security and premission | Samira Azizi | 2026-10-11 | 2026-10-14 | 3 | Not Started | Protect password and restrict access by role | Complete
#003 - Create and update donor profiles | Samira Azizi | 2026-10-12 | 2026-10-14 | 3 | Not Started | Allow donors to create and edit profiles | In Progress
#004 - Blood type and availability fields | Samira Azizi | 2026-10-12 | 2026-10-13 | 3 | Not Started | Store blood type and availability
#005 - Change availability status | Samira Azizi | 2026-10-13 | 2026-10-14 | 2 | Not Started | Allow donors to mark themselves as available or unavailable
#024 - Input validation and error handling | All developers | 2026-10-12 | 2026-10-15 | 4 | Not Started | Validate forms and display errors
#025 - Initial test cases and track defects | All developers | 2026-10-12 | 2026-10-16 | 3 | Not Started | Test registration, login, and profiles
SPRINT 2 - Search and map | All team | 2026-10-15 | 2026-10-18 | 4 | Not Started | Implement donor discovery and location features
#006 - Search donors by blood type | Ahmad Kaihan Saba | 2026-10-15 | 2026-10-17 | 3 | Not Started | Show donors matching the selected blood type
#007 - Search by location or distance | Ahmad Kaihan Saba | 2026-10-15 | 2026-10-18 | 4 | Not Started | Filter donord based on their location or distance
#009 - Display approximate locations | Ahmad Kaihan Saba | 2026-10-15 | 2026-10-17 | 3 | Not Started | Avoid revealing exact home addresses
#023 - Protect donor privacy | Samira Azizi, Ahmad Kaihan Saba | 2026-10-15 | 2026-10-18 | 4 | Not Started | Restrict access to private information
#008 - Interactive map | Ahmad Kaihan Saba | 2026-10-16 | 2026-10-18 | 3 | Not Started | Show approved medical facilities
#010 Create and send blood requests | Shafiqa Taraki | 2026-10-16 | 2026-10-18 | 3 | Not Started | Allow blood seekers to create blood requests
#024 Input validation and error handling | All developers | 2026-10-15 | 2026-10-18 | 4 | Not Started | Validate search and request inputs
#025 - Search, privacy, and request testing | All developers | 2026-10-16 | 2026-10-18 | 3 | Not Started | Test filters, privacy, and request creation
SPRINT 3 - Request responses and communication | All team | 2026-10-19 | 2026-10-23 | 5 | Not Started | Complete the blood request flow
#011 - Blood request notifications | Shafiqa Traki | 2026-10-19 | 2026-10-20 | 2 | Not Started | Notify donors about requests
#012 - Accept or decline requests | Shafiqa Traki | 2026-10-19 | 2026-10-21 | 3 | Not Started | Let donors accept or decline requests
#013 - Display donor responses | Shafiqa Traki | 2026-10-20 | 2026-10-21 | 2 | Not Started | Show the response to the seeker
#014 - Messaging after request acceptance | Shafiqa Traki | 2026-10-20 | 2026-10-22 | 3 | Not Started | Enable messaging only after acceptance
#024 - Input validation and error handling | All developers | 2026-10-19 | 2026-10-23 | 5 | Not Started | Handle invalid requests and communication errors
#025 - Integration and defect retesting | All developers | 2026-10-20 | 2026-10-23 | 4 | Not Started | Record defects and retest fixes
Requirements Specification | Madina Pasun and team | 2026-10-19 | 2026-10-23 | 5 | Not Started | Document functional and non-functional requirements
Use Case Diagram | All developers | 2026-10-19 | 2026-10-21 | 3 | Not Started | Show system use cases
Sequence Diagram | All developers | 2026-10-20 | 2026-10-23 | 4 | Not Started | Illustrate workflow
SPRINT 4 - Finalization and Submission | All team | 2026-10-24 | 2026-10-26 | 3 | Not Started
#015 - Donation History | Samira Azizi | 2026-10-24 | 2026-10-26 | 3 | Not Started | Allow users to see their donation records
#016 - Manage account information | Samira Azizi | 2026-10-24 | 2026-10-25 | 2 | Not Started | Allows users to update account information
#017 - Admin manages registered users | Shafiqa Taraki | 2026-10-24 | 2026-10-26 | 3 | Not Started | Provide authorized management control
#018 - Admin manages hospitals and clinics | Shafiqa Taraki | 2026-10-24 | 2026-10-26 | 3 | Not Started | Add, update, and remove facility information
#019 - Admin reviews reported accounts | Shafiqa Taraki | 2026-10-24 | 2026-10-26 | 3 | Not Started | Review reports
#020 Admin monitors requests and platform activities | Shafiqa Taraki | 2026-10-24 | 2026-10-26 | 3 | Not Started | Provide an overview of requests and platform activity
#024 - Final validation and error handling | All developers | 2026-10-24 | 2026-10-26 | 3 | Not Started | Check validation and error handling across the application
#025 - Final testing | All developers | 2026-10-24 | 2026-10-26 | 3 | Not Started | Test workflow
Finalize product backlog and sprint backlogs | Madina Pasun | 2026-10-24 | 2026-10-25 | 2 | Not Started | Ensure that the backlogs reflect the actual work
Meeting minutes and burn down chart | Madina Afshar | 2026-10-24 | 2026-10-25 | 2 | Not Started | Organize meeting records and data
GitHub repository and documentation review | All team | 2026-10-24 | 2026-10-25 | 2 | Not Started | Check codes, diagrams, backlogs, and all the other documentations
Final demo | All team | 2026-10-24 | 2026-10-26 | 3 | Not Started | Prepare the project deliverables and submit